## No Dates
|  |  | January | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
Phase |  | Tasks | 26-30 | 2-6 | 9-13 | 16-20 | 23-27 | 2-6 | 9-13 | 16-20 | 23-27 | 6-10 | 13-17 | 20-24 | 27-1 | 4-8 | 11-15 | 18-22 | 25-29 | 8-12 | 15-19 | 22-26 | 29-3 | 6-10 | 13-17 | 20-24 | 27-31
1 | Programmer Recruitment
Define Role & Skills
Advertise & Collect Applications
Evaluate Candidates & Interviews
Select & Onboard Programmer
2 | Requirements & Data
Analyse Client Data
Refine Requirements
3 | System & Interface Design
Design System Architecture
GUI Design
Design Finalised
4 | Feature Development
Prepare Presentation
Internal Presentation
Fleet Tracking
Cargo Tracking
Fuel Monitoring
5 | Demo Preparation
Final Feature Integration
System Validation
Demo Software
Demo Ends
8 | Delivery
Deliver Final Software
Final Software
Legend
Phase
Task
Milestone
Client Meeting
Deliverable

## With Dates
|  |  | January | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
|  |  | 26-30 | 2-6 | 9-13 | 16-20 | 23-27 | 2-6 | 9-13 | 16-20 | 23-27 | 6-10 | 13-17 | 20-24 | 27-1 | 4-8 | 11-15 | 18-22 | 25-29 | 8-12 | 15-19 | 22-26 | 29-3 | 6-10 | 13-17 | 20-24 | 27-31
Phase |  | Tasks
1 | Programmer Recruitment | bar: February 2-6 to February 16-20
Define Role & Skills | bar: February 2-6
Advertise & Collect Applications | bar: February 2-6 to February 16-20
Evaluate Candidates & Interviews | bar: February 9-13 to February 23-27
Select & Onboard Programmer | bar: February 23-27 to March 2-6
2 | Requirements & Data
Analyse Client Data | bar: March 9-13
Refine Requirements | bar: March 9-13 to March 16-20
3 | System & Interface Design
Design System Architecture | bar: March 23-27 to April 6-10
GUI Design | bar: April 6-10 to April 13-17
4 | Feature Development
Prepare Presentation | bar: April 20-24 to April 27-1
Fleet Tracking | bar: April 20-24 to May 11-15
Cargo Tracking | bar: April 27-1 to May 18-22
Fuel Monitoring | bar: May 4-8 to May 18-22
5 | Demo Preparation
Final Feature Integration | bar: May 25-29
System Validation | bar: June 8-12
8 | Delivery
Deliver Final Software | bar: June 22-26 to July 27-31
Project Start
01/02
16/03
20/04
18/05
22/06
Design Finalised
01/02
20/07
Internal Presentation
01/05
Demo
12/06
Demo Ends
01/02
Final Software
12/06
Legend
Phase
Task
Milestone
Client Meeting
Deliverable
16/02